## Consolidated
PO Bot | Requirement/Change/Issue | Status/Progress | Date of Update | Owner/Reference | Heads | Users | Comment | Heads 2 | Users 2
Signet | Released for UAT | UAT in progress | Dec 4, 2025` | Yajuvendra Singh |  |  | Emperor slowness issue at user end. | Mili | Yajuvendra, Chintan and Sushil
Signet | 1. The suffix will be taken changed to SKU numbers by the IG Team |  | 2025-12-12 | Sales Team | Mili | Yajuvendra | Chintan and Sushil
Signet | 2. Update regarding master SKU as in the PO file size wise SKU the decison pending from IG |  | 2025-12-15 | Sales Team
Sterling & Walmart | Automation Walkthrough | Completed | 2025-12-12 | Algorisys Team |  |  | Demo done
Walmart | 1. Use item number as a suffix IG team will update the item number as suffix and 2. For sterling buyer number as a suffix will be updated by sales team | - | 2025-12-12 | Sales Team |  |  |  | Hetal | Nimay, Dipika
Sterling | 3. Logic: Use buyer number to find reference design code when style is unknown 4. For sterling the dates are with the 7 days gap. | Script Change Completed | 2025-12-12 | Algorisys Team |  |  |  | Rishul | Bharat, Tahir and Sanvi
Walmart | 5. Logic: Calculate production & export due dates (Order Creation Date + 4 Weeks) | Script Change Completed | 2025-12-12 | Algorisys Team
MHJ | Logic: Separate lab-grown and natural products into different order entries | Script Change Completed | 2025-12-12 | Algorisys Team |  |  |  | Hetal | Ajinkya Vinayak Nilesh
MHJ | Extract order type, customer code, and PO number from file name | Script Change Completed | Completed Walkthrough: Dec 16, 2025 | Algorisys Team
MHJ | Do not update the size field (remain as fetched from PDCM) | Script Change Completed | Completed Walkthrough: Dec 16, 2025 | Algorisys Team
MHJ | Create separate file for Lab-Grown Diamond orders during processing | Change Completed | Completed Walkthrough: Dec 16, 2025 | Algorisys Team
MHJ | Commodity Rates Mapping: Update logic to ensure Commodity Rates are aligned with LMG Rates. Replace Unit Price with Sales Price across the data processing workflow. Price Segregation Logic: Use the values G, D, and PT to segregate prices accordingly during processing. | Change Request | Latest Request: Dec 16, 2025 | Algorisys Team
Fraser Heart, Bevilles, Warren James | PO Bot Development Priority | Script Completed | - | Algorisys Team
Ashi, Christ, Doro, LPH | BOT scripting complated | Script Completed | - | Algorisys Team
FH | [6 empty] | Demo done | Vinod | Vinod, Ajinkya
Bevilles | [6 empty] | Demo done | Vinod
WJ |  |  | 22/12/2025 | Algorisys Team |  |  | Demo done | Sachin | Chandraprakash
ASHI |  |  | 22/12/2025 | Algorisys Team |  |  | Demo done | Hetal | Dipika
Christ | [7 empty] | Mili | Sachin Bhosale, Manisha
Doro | [7 empty] | Mili | Sachin Bhosale, Manisha
LBH | [7 empty] | Vinod
Thoms | BOT scripting completed
horizon | BOT scripting completed
stroili | BOT scripting completed

## UAT Status
PO Type | PDF Extraction Status | RPA Scripting Status | UAT Testing | PO User | UAT Date
Signet PO | Completed | Completed | In Progress |  | 2025-12-04
MHJ PO | Completed | Completed | In Progress |  | 2025-12-12
Rosy Sterling | Completed | Completed | In Progress |  | 2025-12-22
WM Order | Completed | Completed | In Progress |  | 2025-12-22
Ashi IG SPO | Completed | Completed | In Progress |  | 2025-12-22
Waren James | Completed | Completed | In Progress |  | 2025-12-22
Bevilles - Fine Jewellery Retail AU | Completed | Completed | In Progress |  | 2025-12-22
Christ Orders | Completed | Completed | Not Started
Doro Order | Completed | Completed | Not Started
FH PO | Completed | Completed | In Progress |  | 2025-12-22
LBH PO | Completed | Completed | In Progress |  | 2025-12-22
Thomo PO - Horizon | Completed | Completed | Not Started
Thomo PO - Thom Sas | Completed | Completed | Not Started
Thomo PO - Stroili Oro S.p.A. | Completed | Completed | Not Started
Aranyagomb Order | Query | Query | Not Started
Sr. No | Requirement (Sales PO) | UAT Status | Remark
1 | Signet PO | UAT WIP | Awaiting for the user feedback
2 | Ashi IG SPO | UAT WIP | Awaiting for the user feedback
3 | Warren James | UAT WIP | Cert type of orders insertion logic
4 | Bevilles -Fine Jewellery Retail AU | UAT Done | User sign off given on 07/01/2026
5 | Christ Orders | Changes in progress | Changes discussed on 07/01/2026
6 | Doro Order | Changes in progress | Changes discussed on 07/01/2026
7 | FH PO (Fraser Hart) | UAT WIP | Awaiting for the user feedback
8 | LBH PO | UAT WIP | Awaiting for the user feedback
9 | Rosy STRL (Sterling) | UAT WIP | Awaiting for the user feedback (User do not had EmrTst access)
10 | Thomo PO- Horrizon | Changes in progress | Changes discussed on 07/01/2026
11 | Thomo PO- Thom Sas | Changes in progress | Changes discussed on 07/01/2026
12 | Thomo PO- Stroili Oro S.p.A. | Changes in progress | Changes discussed on 07/01/2026
13 | MHJ PO | UAT Done | User sign off given on 07/01/2026
15 | WM Order (Wall mart) .rtl file | UAT Done | User sign off given on 05/01/2025

## MHJ
Sr. no. | Requirement/Change/Issue | Status / Progress | Date of Update / change Requested | Walkthrough Done | Owner/Reference | Comment | Post Action
1 | Logic: Separate lab-grown and natural products into different order entries | Script Change Completed | 2025-12-12 | TRUE | Algorisys Team
2 | Extract order type, customer code, and PO number from file name | Script Change Completed | 2025-12-16 | TRUE | Algorisys Team
3 | Do not update the size field (remain as fetched from PDCM) | Script Change Completed | 2025-12-16 | TRUE | Algorisys Team
4 | Create separate file for Lab-Grown Diamond orders during processing | Script Change Completed | 2025-12-16 | TRUE | Algorisys Team
5 | Commodity Rates Mapping: Update logic to ensure Commodity Rates are aligned with LMG Rates. Replace Unit Price with Sales Price across the data processing workflow. Price Segregation Logic: Use the values G, D, and PT to segregate prices accordingly during processing. | Change Requested | 2025-12-16 | FALSE | Algorisys Team
6 | Updated the code to ensure correct style selection from PDCM. | Script Change Completed | 2025-12-22 | TRUE | Algorisys Team
7 | For Sets, may contain same SKU no but Design No. will be different. Fetch all with same SKU and enter in EMR. Price must be divided and item must be increase | Script Change Completed | 2025-12-26 | TRUE | Algorisys Team

## Walmart
Sr. no. | Requirement/Change/Issue | Status / Progress | Date of Update / change Requested | Walkthrough Done | Owner/Reference | Comment | Post Action
1 | Automation Walkthrough | Completed | 2025-12-12 | TRUE | Algorisys Team
2 | Use item number as a suffix IG team will update the item number as suffix and | Script Change Completed | 2025-12-12 | TRUE | Sales Team
3 | For sterling buyer number as a suffix will be updated by sales team | Script Change Completed | 2025-12-12 | TRUE | Sales Team
4 | Calculate production & export due dates (Order Creation Date + 4 Weeks) | Script Change Completed | 2025-12-12 | TRUE | Algorisys Team
4 | For Sets, may contain same SKU no but Design No. will be different. Fetch all with same SKU and enter in EMR. Price must be divided and item must be increase | Script Change Completed | 2025-12-26 | TRUE | Algorisys Teams

## Warren J.
Sr. no. | Requirement/Change/Issue | Status / Progress | Date of Update / change Requested | Walkthrough Done | Owner/Reference | Comment | Post Action
1 | Shown a walkthrough | Completed | 2025-12-22 | TRUE | Algorisys Team
2 | PO Date will be the date of creation of the order. | Script Change Completed | 2025-12-22 | TRUE | Algorisys Team
3 | Production Delivery Date and Expected Delivery Date will both be 2 weeks from the order creation date. | Script Change Completed | 2025-12-22 | TRUE | Algorisys Team
4 | A new bulk PO file has been provided; the extractor needs to be updated as per the new format | Script Change Completed | 2025-12-22 | TRUE | Algorisys Team
5 | Cert orders types of oders are getting seperated need a logic to add the add the cert type of orders. | Change Requested | 2026-01-09 | TRUE | Algorisys Team

## Frazer Heart
Sr. no. | Requirement/Change/Issue | Status / Progress | Date of Update / change Requested | Walkthrough Done | Owner/Reference | Comment | Post Action
1 | Initial WalkThrough | Completed | 2025-12-22 | TRUE | Algorisys Team
2 | SKU size extraction needs to be updated according to the bulk order format. | Script Change Completed | 2025-12-22 | TRUE | Algorisys Team
3 | Export Delivery Date will be extracted directly from the PO | Completed | 2025-12-22 | TRUE | Algorisys Team
4 | Production Delivery Date will be 10 days prior to the Export Delivery Date | Completed | 2025-12-22 | TRUE | Algorisys Team
5 | Excel File Extraction from PDF file | Completed | 2025-12-26 | TRUE | Algorisys Team
6 | Scripting to Enter Data in EMR | Completed | 2025-12-26 | TRUE | Algorisys Team

## Bevilles
Sr. no. | Requirement/Change/Issue | Status / Progress | Date of Update / change Requested | Walkthrough Done | Owner/Reference | Comment | Post Action
1 | Initial WalkThrough | Completed | 2025-12-22 | TRUE | Algorisys Team
1 | Logic will be updated so that the user can directly provide an Excel file, and PO bot execution will be based on this Excel input. | Completed | 2025-12-22 | TRUE | Algorisys Team
2 | Export Delivery Date will be 3 days prior to the Requested Delivery Date | Completed | 2025-12-22 | TRUE | Algorisys Team
3 | Production Delivery Date will be 7 days prior to the Export Delivery Date. | Completed | 2025-12-22 | TRUE | Algorisys Team

## Ashi
Sr. no. | Requirement/Change/Issue | Status / Progress | Date of Update / change Requested | Walkthrough Done | Owner/Reference | Comment | Post action
1 | Initial WalkThrough | Completed | 2025-12-22 | TRUE | Algorisys Team | may contain multiple POs
2 | Purchase Order Date will be the creation date | Completed | 2025-12-22 | TRUE | Algorisys Team
3 | SPO type POs: Production Delivery Date and Export Delivery Date = PO Date + 2 weeks | Completed | 2025-12-22 | TRUE | Algorisys Team
4 | COM type POs: Production Delivery Date and Export Delivery Date = PO Date + 4 weeks. | Completed | 2025-12-22 | TRUE | Algorisys Team
5 | Sub-PO details need to be added while inserting line items. | Completed | 2025-12-22 | TRUE | Algorisys Team
6 | may contain multiple POs; this needs to be handled, and extraction logic must be corrected accordingly | Script Change Completed | 2025-12-22 | TRUE | Algorisys Team

## Signet
Sr. no. | Requirement/Change/Issue | Status / Progress | Date of Update / change Requested | Walkthrough Done | Owner/Reference | Comment | Post Action
1 | Initial WalkThrough | Completed | 2025-12-04 | TRUE | Algorisys Team
2 | The suffix will be taken changed to SKU numbers by the IG Team | Script Change Completed | 2025-12-12 | TRUE | Sales Team
3 | Update regarding master SKU as in the PO file size wise SKU the decison pending from IG | Script Change Completed | 2025-12-15 | TRUE | Sales Team
4 | Sales price needed to be updated by Unit Price | Script Change Completed | 2026-01-07 | TRUE | Algorisys Team
5 | Gold lock rates need to be updated as per user ranges given | Query required | 2026-01-07 | FALSE | Sales Team

## Sterling
Sr. no. | Requirement/Change/Issue | Status / Progress | Date of Update / change Requested | Walkthrough Done | Owner/Reference | Comment | Post Action
1 | Initial WalkThrough | Completed | 2025-12-12 | TRUE | Algorisys Team
2 | Logic: Use buyer number to find reference design code when style is unknown | Completed | 2025-12-12 | TRUE | Sales Team
3 | For sterling the dates are with the 7 days gap. | Completed | 2025-12-12 | TRUE | Sales Team
4 | For sterling the dates are with the 14 days gap. | Script Change Completed | 2026-01-07 | TRUE | Algorisys Team
5 | Use vendor number to get IG Style code | Script Change Completed | 2025-12-26 | TRUE | Algorisys Team
6 | Access issue in the user EMR login | NA | 2026-01-09 | FALSE | Sales Team

## Thoms_Stroili
Sr. no. | Requirement/Change/Issue | Status / Progress | Date of Update / change Requested | Walkthrough Done | Owner/Reference | Comment | Post Action
1 | Initial WalkThrough | Completed | 2026-01-07 | TRUE | Algorisys Team
2 | Export Date and Prediction Date to be decide | Change Requested | 2026-01-07 | FALSE | Algorisys Team
3 | Make exe file to separate LGD and Mined diamonds into different excels | Change Requested | 2026-01-07 | FALSE | Algorisys Team
4 | Refresh Rates of comodities | Change Requested | 2026-01-07 | FALSE | Algorisys Team
5 | New PO/s has do be send by the user | client requirement | 2026-01-07 | FALSE | Sales Team

## Horizon
Sr. no. | Requirement/Change/Issue | Status / Progress | Date of Update / change Requested | Walkthrough Done | Owner/Reference | Comment | Post Action
1 | Initial WalkThrough | Not Started |  | FALSE | Algorisys Team
2 | Export Date and Prediction Date to be decide | Not Started |  | FALSE | Sales Team
3 | PO provided contain Style code which is recognized/ has access | client Requirement |  | FALSE | Sales Team

## Christ
Sr. no. | Requirement/Change/Issue | Status / Progress | Date of Update / change Requested | Walkthrough Done | Owner/Reference | Comment | Post Action
1 | Initial WalkThrough | Completed | 2026-01-07 | TRUE | Algorisys Team
2 | PO Date = Current Date, Exp. date = Arrival Date (Excel) - 1 week, Prd. date = Exp. Date - 1 week | Change Requested | 2026-01-07 | FALSE | Algorisys Team
3 | Batch No. = SKU and SubPo no. needed to be enter | Change Requested | 2026-01-07 | FALSE | Sales Team
4 | Refresh Rate need to be updated by previous date + 4.5$ | Change Requested | 2026-01-07 | FALSE | Algorisys Team

## Doro
Sr. no. | Requirement/Change/Issue | Status / Progress | Date of Update / change Requested | Walkthrough Done | Owner/Reference | Comment | Post Action
1 | Initial WalkThrough | Completed | 2026-01-07 | TRUE | Algorisys Team
2 | PO Date = Current Date, Exp. date = Arrival Date (Excel) - 1 week, Prd. date = Exp. Date - 2 week | Change Requested | 2026-01-07 | FALSE | Algorisys Team
3 | Batch No. = SKU and SubPo no. needed to be enter | Change Requested | 2026-01-07 | FALSE | Sales Team
4 | Refresh Rate need to be updated by previous date + 4.5$ | Change Requested | 2026-01-07 | FALSE | Algorisys Team

## Thoms
Sr. no. | Requirement/Change/Issue | Status / Progress | Date of Update / change Requested | Walkthrough Done | Owner/Reference | Comment | Post Action
1 | Initial WalkThrough | Completed | 2026-01-07 | TRUE | Algorisys Team
2 | Export Date and Prediction Date to be decide | Script Change Completed | 2026-01-07 | FALSE | Algorisys Team
3 | Make exe file to separate LGD and Mined diamonds into different excels | Script Change Completed | 2026-01-07 | FALSE | Algorisys Team
4 | Refresh Rates of comodities | Change Requested | 2026-01-07 | FALSE | Algorisys Team