## Sheet1
Sr. No | Requirement (Sales PO) | UAT Status | Remark
1 | Signet PO | UAT WIP | To review in 2nd Week of Jan
2 | Ashi IG SPO | Changes Completed | Awaiting for the UAT release
3 | AV-PO | Not Required
| Warren James | UAT WIP
4 | Bevilles -Fine Jewellery Retail AU | UAT WIP | Minor Changes discussed & Completed on 26-Dec
5 | Christ Orders | UAT Release Awaited | To schedule in 2nd Week of Jan
6 | Doro Order | UAT Release Awaited | To schedule in 2nd Week of Jan
7 | FH PO (Fraser Hart) | UAT WIP
8 | LBH PO | UAT WIP | Completed on 26-Dec
9 | Rosy STRL (Sterling) | UAT WIP | Completed on 30-Dec
10 | Thomo PO- Horrizon | Changes in progress | Changes discussed on 26-Dec
11 | Thomo PO- Thom Sas | Changes in progress | Changes discussed on 26-Dec
12 | Thomo PO- Stroili Oro S.p.A. | Changes in progress | Changes discussed on 26-Dec
13 | VA | Not Required | Confirmed on 26-Dec
14 | Aranyagomb Order | Not on Priority | Confirmed on 26-Dec
15 | MHJ PO | UAT WIP | Minor Changes discussed on 26-Dec (WIP)
16 | WM Order (Wall mart) .rtl file | UAT WIP | Minor Changes discussed & Completed on 26-Dec